## Guidelines
The Engineer Accelerator
Professional Work Process
Name | Name
Verision | 0.1
Work Process | Version Control Process | Error Mitigation Stratagy | Work Day Guidelines | Repsonsibility Guidelines | Communication Guidelines | Conflict Resolution Stratagy
|  |  | Standard | Manager | Email
1. stake holder meeting / expectation setting | 1. Document with new information requires revision change | 1. Use review checklist to ensure work for current stage is complete | 8 hrs - 10 hrs | Provide guidelines, liasion between client and project. Define expectation, budget , schedule Highlight Risk Define standards | 1. Formal Notification , reporting | 1.meetings with respective stakeholders
2 resourses organization / team/ product design, development plan for standards, features , scalability , future features, new technology , existing technology / execution strategy | 2. work to proceed only after approval | 2. prototype testing , software testing , functional test, system tests |  |  | 2. Formal request | 2. Risk evaluation, solution, options
|  |  | Extended |  |  | 3. Path forward
|  | 3. randome sample testing (sample size 10, ie 1 out of 10) + all above tests | 10 hrs - 16 hrs |  |  | 4. Agreement and effect of change on project
You
|  | 4. randome sample testing ( sample size 100) |  | design, develop , maintain records & documents , review , test assigned product to manager based on set requirements by manager | Chat
|  |  | All Nighter |  | 1. For opinions
3. Budget / Project cost control |  | 5. Alignemt meetings with team, manager etc. | 16 hrs and above |  | 2 Information sharing
4. Schedule |  |  |  |  | 3. Informal project communication
5. Project risk / Mitigation
6. Quality expectation / Testing / document control |  |  |  |  | Phone
7. Lessons learnt / Future Improvements |  |  |  | Colleague | 1. organization of work , communicate expected requirements, workflow, meeting, discussions
Review , critique , feedback
Video
1. conferences meetings, discussion , reviews,
2. meetings
Meeting
1. reviews
2. discussion
3. decision making
4. progress
5. all other project communications

## Review Check List
Review Check List
| Product developer | Manager
Product Definition
Version | 0 | 0 | 0 | Legend No go => implies more work required cannot proceed , use '0' to indicate a no go situation Go => implies ready to go to next stage use '1' to indicate a situation where product development can proceed to next stage
Archiecture
Version | 0 | 0 | 0
Schematic
Version | 0 | 0 | 0
Layout
Version | 0 | 0 | 0
BOM
Version | 0 | 0 | 0

## Release Checklist
Release Check List
Product Definition
Archiecture
Schematic
Layout
BOM